## Overview
Naavik Unified UX — Feature Roadmap
Living document. One row per domain; click a sheet tab for the full feature list.
Domain | Features | Built | In Progress | Planned | P0/P1 | Sheet
Platform & Auth | [5 empty] | → Platform & Auth
Chat & Intent | [5 empty] | → Chat & Intent
Naavik Observe | [5 empty] | → Naavik Observe
Naavik AppGen | [5 empty] | → Naavik AppGen
Naavik Provision | [5 empty] | → Naavik Provision
Control Agent | [5 empty] | → Control Agent
Knowledge Library | [5 empty] | → Knowledge Library
Generative UI | [5 empty] | → Generative UI
Data Layer | [5 empty] | → Data Layer
Settings | [5 empty] | → Settings
Demo Mode | [5 empty] | → Demo Mode
TOTAL
Legend
Status colors
Built
In Progress
Planned
Backlog
Deferred
Priority colors
P0
P1
P2
P3

## Platform & Auth
Platform & Auth
11 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
PF-001 | JWT Login + 4-hour Persistent Session | Username/password login with bcrypt + JWT. Token stored in localStorage. Frontend re-verifies on reload. | Built | P0 | Approved | Auth Team | S | v1.0 | Q1 2026 | — | Live in prod
PF-002 | Env-Driven Admin Credentials | Admin user/password/JWT secret read from .env. Lazy init handles ESM hoisting timing. Fails fast on missing config. | Built | P0 | Approved | Auth Team | S | v1.0 | Q1 2026 | PF-001 | Hardened recently
PF-003 | Auth Context + Permission Gating | AuthContext exposes user + per-app permissions. Components gate features via useAuth(). Permissions auto-refresh on user change. | Built | P0 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | PF-001
PF-004 | First-Time Market Selector Modal | Non-dismissable modal blocks app on first login until market is picked. Subsequent logins skip it. Persisted to localStorage. | Built | P1 | Approved | Frontend Platform | S | v1.1 | Q2 2026 | PF-005
PF-005 | Multi-Market Configuration | Markets config in frontend/src/config/markets.ts. NorCal live; SoCal/PNW/TX/NE shown as 'Coming soon'. Maps labels to remote MARKET values. | Built | P1 | Approved | Frontend Platform | S | v1.1 | Q2 2026 | — | More markets pending data
PF-006 | Theme Provider (Light/Dark) | ThemeProvider exposes theme + setTheme. All bespoke components consume it. Defaults to dark; html.dark forced on bootstrap. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | —
PF-007 | User Profile Dropdown | Sidebar avatar opens consolidated menu — Market / Settings / Feedback / Logout. Inline when expanded; portal popover when collapsed. | Built | P1 | Approved | Frontend Platform | S | v1.1 | Q2 2026 | PF-005, ST-001
PF-008 | Collapsible Left Sidebar | Claude-style sidebar with collapse/expand, navigation rail, per-stream session history, profile menu at bottom. | Built | P1 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | —
PF-009 | Platform Bus (Inter-App Navigation) | Pub/sub bus for navigation intents (NAVIGATE_TO_APP). Shell subscribes and routes. Used by chat to deep-link into apps. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | —
PF-010 | App Registry | Dynamic registry of mountable apps with display name, icon, route, default chat stream, permission key. Drives sidebar nav and AppSlot. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | PF-009
PF-011 | Login UI with Fluid Background | Split-pane layout, animated fluid gradient background, theme-aware Naavik branding. Username + password + show/hide toggle. | Built | P2 | Approved | Design | S | v1.0 | Q1 2026 | PF-001

## Chat & Intent
Chat & Intent
15 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
CI-001 | Multi-Stream Chat Orchestrator | Five chat streams (universal, observability, appgen, provision, knowledge) with stream-specific prompts and starter suggestions. | Built | P0 | Approved | Agent Team | M | v1.0 | Q1 2026 | —
CI-002 | Agent V3 Orchestrator | True OpenAI function-calling loop. Tools execute in parallel via Promise.allSettled. MAX_ITERATIONS=8, model gpt-4o-mini. | Built | P0 | Approved | Agent Team | L | v1.1 | Q2 2026 | —
CI-003 | 21-Tool Agent Registry | Tools include find_site, get_worst_offenders, RCA, KPI dashboard, query_data, generate_report, knowledge, navigation. | Built | P0 | Approved | Agent Team | L | v1.0 | Q1 2026 | CI-002
CI-004 | Site-Analysis Tool Suite (10 tools) | topology, config_changes, neighbor_relations, ret_changes, site_outages, neighbor_outages, hourly_trends, kpi_impact_breakdown, ticket_history, compare_with_cluster. | Built | P0 | Approved | Agent Team | XL | v1.1 | Q2 2026 | DL-002
CI-005 | Intent Classifier | Semantic + explicit + context-aware classifier. Routes 'show map', 'explain RCA', 'build app' to the right stream and tool path. | Built | P1 | Approved | Agent Team | M | v1.0 | Q1 2026 | —
CI-006 | Navigation Orchestrator | Three-layer intent detection turning chat into platform-bus events. 'Open observe' navigates; 'sites with alarms' also sets map layer. | Built | P1 | Approved | Agent Team | M | v1.0 | Q1 2026 | PF-009, CI-005
CI-007 | Conversation Context Service | Persists thread state, history, metadata in PostgreSQL. Multi-turn conversations work across reloads. | Built | P1 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
CI-008 | Stop Button (Abort Controller) | Send button morphs into Stop with spinning ring. Click aborts in-flight agentV3Chat via AbortController. Posts silent 'Request stopped' note. | Built | P1 | Approved | Frontend Platform | S | v1.2 | Q2 2026 | CI-002
CI-009 | Structured Synthesis Format | System prompt requires six-section markdown synthesis. Powers DiagnosisCard. Severity / Headline / What Changed / Degraded / Root Cause / Next Actions. | Built | P1 | Approved | Agent Team | S | v1.2 | Q2 2026 | CI-002
CI-010 | Auto-Emit Diagnosis Card | Orchestrator detects structured synthesis, injects diagnosis_card UI block, replaces chat-bubble text with just the headline. | Built | P1 | Approved | Agent Team | M | v1.2 | Q2 2026 | CI-009, UI-018
CI-011 | KPI / Parameter Resolver | resolve_kpi_param tool fuzzy-matches user phrases against the 16k DataDict catalog. Surfaces chip selector when ambiguous. | Built | P1 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | KN-002
CI-012 | Suggestion Chips & Starter Prompts | Each chat stream has curated suggestions. Empty state shows starter chips. Home rotates placeholders. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | —
CI-013 | Multi-Attachment Support | Up to 3 attachments per message — CSVs ≤750KB, images ≤900KB, text ≤120KB. Sent inline with chat payload. | Built | P2 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | —
CI-014 | Per-Stream Session History | Sidebar shows recent prompts grouped by stream. Click to re-send. History local to React state (not yet persisted). | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | — | Persistence planned for v1.3
CI-015 | V2 Chat Fallback | Legacy V2 orchestrator (no tool calling) as fallback. Toggle via localStorage or Settings. | Built | P3 | Approved | Agent Team | S | v0.9 | Q4 2025 | — | Will be deprecated in v2.0

## Naavik Observe
Naavik Observe
22 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
OB-001 | Mapbox Site Map | Interactive Mapbox-GL map showing 6,800+ sites for selected market. Zoom/pan/click. Color-coded by severity. | Built | P0 | Approved | Observe Team | L | v1.0 | Q1 2026 | DL-014
OB-002 | Site Layer Toggles | Three layers — degraded, outage, overutilized. Driven by set_map_layer from chat or direct UI clicks. | Built | P0 | Approved | Observe Team | M | v1.0 | Q1 2026 | OB-001
OB-003 | Site Detail Panel — 5 Tabs | Click site → tabbed panel. Site KPI, RCA, Operational, Topology, AI Analyzer. Summary vs Diagnostic mode toggle. | Built | P0 | Approved | Observe Team | L | v1.1 | Q2 2026 | OB-001
OB-004 | Summary Mode (Animated RCA) | RCA-focused summary with step-by-step strongest-factors animation, mini-map for related neighbors. | Built | P1 | Approved | Observe Team | M | v1.0 | Q1 2026 | OB-003
OB-005 | Diagnostic Mode | Full telemetry — KPI charts, hourly insights, anomaly callouts. Sub-second loads via local mirror. | Built | P0 | Approved | Observe Team | L | v1.2 | Q2 2026 | DL-002, DL-012
OB-006 | Cell Topology View | Cells listed with band, technology, azimuth, height, anomaly. Replaced by TopologyGrid (band tiles). | Built | P1 | Approved | Observe Team | M | v1.2 | Q2 2026 | UI-020
OB-007 | KPI Dashboard (Daily/Hourly) | Multi-KPI line-chart with daily 7-90d / hourly 24-72h. KPI selector with 16 grouped standard KPIs + custom search. | Built | P0 | Approved | Observe Team | L | v1.0 | Q1 2026 | DL-015
OB-008 | Multi-KPI Comparison | Up to 8 KPIs simultaneously, unit-aware Y-axis, anomaly markers, shared 20-color palette. | Built | P1 | Approved | Observe Team | M | v1.0 | Q1 2026 | OB-007
OB-009 | Hourly Insights Panel | Time-of-day pattern analysis — peak hours, busy-hour deviation, anomaly hours, weekly comparison. | Built | P1 | Approved | Observe Team | M | v1.1 | Q2 2026 | OB-007
OB-010 | Mobility Trends | HOSR, inter/intra-frequency HO, throughput-per-handover. Used by analyzer for coverage detection. | Built | P2 | Approved | Observe Team | M | v1.1 | Q2 2026 | —
OB-011 | Outage Timeline | Per-cell outage events on 24h or 7d strip. Shows metric type and snapshot hour. | Built | P2 | Approved | Observe Team | M | v1.1 | Q2 2026 | —
OB-012 | Traffic Profile Dashboard | DL/UL volume + PRB-utilisation profile. Distinguishes capacity from coverage issues. | Built | P2 | Approved | Observe Team | M | v1.1 | Q2 2026 | —
OB-013 | Cross-Correlator (KPI Relationships) | Pairwise correlation between KPIs. Surfaces which pairs move together or diverge. | Planned | P2 | Pending | Observe Team | L | v1.4 | Q3 2026 | OB-007 | Removed for redesign
OB-014 | AI Analyzer Tab | Dedicated tab in site detail. Runs deep investigation (8-10 tools parallel). Hero severity card + 4 verdict sections + trail + evidence. | Built | P0 | Approved | Agent Team | L | v1.2 | Q2 2026 | CI-002, CI-004
OB-015 | Worst Offenders Ranking | Daily ranked list by total CQX impact. Each row links to site detail. Inline 'Explain RCA' button. | Built | P0 | Approved | Observe Team | M | v1.0 | Q1 2026 | DL-002
OB-016 | Cluster Comparison | Site KPI vs cluster peers. Returns rank, percentile, outlier flag (>2σ). Bar chart with source highlighted. | Built | P1 | Approved | Agent Team | M | v1.2 | Q2 2026 | CI-004
OB-017 | Neighbor Map Overlay | Top neighbors as dashed lines on map with HO-share labels. Click pivots panel to that site. | Built | P1 | Approved | Observe Team | M | v1.1 | Q2 2026 | OB-001, OB-003
OB-018 | Operational Info Workbench | Aggregates alarms, tickets, config, outages, EIM for site + neighbors over 7d. Sub-tabs per type. | Built | P1 | Approved | Observe Team | L | v1.1 | Q2 2026 | DL-002
OB-019 | Compass Dashboard (KPI Tiles) | Market-level dashboard tile grid showing aggregated KPIs across selected sites. At-a-glance Network Management home. | Built | P1 | Approved | Observe Team | M | v1.0 | Q1 2026 | DL-015
OB-020 | Telemetry Dashboard with Gauges + Heatmaps | Professional 5-tab telemetry — semicircular gauge charts, hourly heatmaps, KPI trend mini-charts. | Built | P1 | Approved | Observe Team | L | v1.1 | Q2 2026 | OB-007
OB-021 | Map Chat Bar | Persistent chat input docked to map view. Pre-fills with selected site's USID for quick 'what's wrong here?' queries. | Built | P1 | Approved | Observe Team | M | v1.0 | Q1 2026 | CI-001
OB-022 | Site Status Pills | TOP DEGRADED / OUTAGE pulse pills in panel header for offender sites. Pulled from cqx_offenders + site.outage. | Built | P2 | Approved | Observe Team | S | v1.0 | Q1 2026 | —

## Naavik AppGen
Naavik AppGen
18 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
AG-001 | 6-Stage AI App Pipeline | Planning → Code Gen → Audit → Unit Test → Integration → Assembly. State machine with backward navigation. | Built | P0 | Approved | AppGen Team | XL | v1.0 | Q1 2026 | —
AG-002 | Planning Agent | Takes NL requirement, produces structured plan: target KPI, trigger, action, scope, failure modes. User approves before code gen. | Built | P0 | Approved | AppGen Team | L | v1.0 | Q1 2026 | AG-001
AG-003 | Code Generation Agent | Generates rApp code, config YAML, K8s manifests, tests. Live file panel updates. Monaco editor for inline edit. | Built | P0 | Approved | AppGen Team | XL | v1.0 | Q1 2026 | AG-002
AG-004 | Code Audit Agent | Static analysis — security (no embedded secrets, safe SQL), correctness (parameter ranges, KPI validity), style. | Built | P1 | Approved | AppGen Team | L | v1.0 | Q1 2026 | AG-003
AG-005 | Unit Test Agent | Generates and runs unit tests in sandboxed runner. Failures surface inline with assertion details. | Built | P1 | Approved | AppGen Team | L | v1.0 | Q1 2026 | AG-003
AG-006 | Integration Validation Agent | End-to-end smoke test against simulated network. Feeds rApp synthetic KPI streams, validates control actions. | Built | P1 | Approved | AppGen Team | L | v1.1 | Q2 2026 | PV-002
AG-007 | App Assembly Agent | Packages code + tests + manifests + metadata into deployable bundle. Produces zip and 'publish to catalog' action. | Built | P1 | Approved | AppGen Team | M | v1.1 | Q2 2026 | AG-013
AG-008 | Conversational App Builder | Free-form chat for app creation. Asks clarifying questions when requirement is ambiguous. | Built | P0 | Approved | AppGen Team | L | v1.0 | Q1 2026 | CI-001
AG-009 | Scaffold Confirmation | Before code gen, agent shows file scaffold (which files, what they contain). User approves or rejects. | Built | P1 | Approved | AppGen Team | M | v1.0 | Q1 2026 | AG-002
AG-010 | Real-Time File Generation Panel | Streamed file writes appear live. Each file shows progress + syntax-highlighted preview when done. | Built | P1 | Approved | AppGen Team | M | v1.0 | Q1 2026 | AG-003
AG-011 | Workflow State Machine + Backward Nav | 6-stage pipeline persists per project. Rewind to any stage, edit, re-run forward. | Built | P1 | Approved | AppGen Team | L | v1.0 | Q1 2026 | AG-001
AG-012 | Multi-Project Workspace | Side-by-side project switcher. Each project keeps own files, conversation, pipeline state. | Built | P2 | Approved | AppGen Team | M | v1.1 | Q2 2026 | AG-001
AG-013 | rApp Packager | Produces Kubernetes-ready chart with values.yaml, deployment, service. Optional cluster-context targeting. | Built | P1 | Approved | AppGen Team | L | v1.1 | Q2 2026 | —
AG-014 | AppGen Catalog with LangChain Reranker | Search-and-clone existing apps. Embeddings + LangChain rerank surface the most relevant prior art. | Built | P1 | Approved | AppGen Team | L | v1.1 | Q2 2026 | —
AG-015 | YANG / DataDict Domain Tools | Validates parameters against YANG models and DataDict catalog. Surfaces 'unknown parameter' warnings. | Built | P1 | Approved | AppGen Team | M | v1.0 | Q1 2026 | KN-002
AG-016 | Interactive Q&A Clarification | Planning agent asks user inline when requirement is unclear. Answers append to running plan. | Built | P1 | Approved | AppGen Team | M | v1.0 | Q1 2026 | AG-002
AG-017 | AppGen Memory System | Per-project conversation memory + cross-project lessons learned. PG-backed, surfaced as suggestions. | Built | P2 | Approved | AppGen Team | M | v1.1 | Q2 2026 | —
AG-018 | Agent Activity Rail | Live progress rail — current agent, tool called, time remaining. Useful for monitoring long pipelines. | Built | P2 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | AG-001

## Naavik Provision
Naavik Provision
6 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
PV-001 | Provisioning Workflow Simulator | Simulates change-management — request, approval, OSS push, validation. No real network impact. | Built | P0 | Approved | Provision Team | L | v1.1 | Q2 2026 | —
PV-002 | OSS Adapter Framework | Pluggable connector interface for ENM, MOSES, etc. Simulator implements the same interface. | Built | P0 | Approved | Provision Team | L | v1.1 | Q2 2026 | —
PV-003 | ENM Connector | Direct integration with Ericsson Network Manager for parameter changes. Feature-flagged per market. | In Progress | P1 | Pending | Provision Team | L | v1.3 | Q3 2026 | PV-002 | Awaiting cred provisioning
PV-004 | Provisioning Candidate Site UI | Sites flagged for parameter changes with current vs proposed values, expected KPI delta, one-click submit. | Built | P1 | Approved | Provision Team | M | v1.1 | Q2 2026 | PV-001
PV-005 | Change Request Flow | Multi-step form: target sites, parameter, old/new values, justification, target window. Integrates rApp builder. | Built | P1 | Approved | Provision Team | L | v1.1 | Q2 2026 | PV-001, AG-001
PV-006 | Provisioning Status Tracking | Status board for in-flight, completed, failed changes. Each row exposes OSS audit log + rollback option. | Built | P1 | Approved | Provision Team | M | v1.1 | Q2 2026 | PV-001

## Control Agent
Control Agent
8 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
CA-001 | Automation Pipeline Service | Backend orchestrator — chat-triggered intent → rApp build → OSS push → KPI validation. PG-persisted state. | Built | P0 | Approved | Agent Team | XL | v1.1 | Q2 2026 | CI-002, AG-001, PV-002
CA-002 | Workflow Generator | High-level goal → executable workflow JSON with steps, triggers, rollback logic. | Built | P1 | Approved | Agent Team | L | v1.1 | Q2 2026 | CA-001
CA-003 | OSS Adapter Simulator | In-process simulator mimicking OSS responses (success/failure, latency, parameter validation). Dev/demo safe. | Built | P1 | Approved | Provision Team | M | v1.1 | Q2 2026 | PV-002
CA-004 | Execution Status Polling | Polls automation status from backend at 2s intervals. Renders in WorkflowExecutionStatus UI block. | Built | P1 | Approved | Frontend Platform | S | v1.1 | Q2 2026 | CA-001, UI-013
CA-005 | Agent Automation Report | Final report after workflow — steps executed, OSS responses, KPI deltas measured, success/failure verdict. | Built | P1 | Approved | Agent Team | M | v1.1 | Q2 2026 | CA-001
CA-006 | Multi-Step Workflow Display | Stage-by-stage UI — each automation step with status (pending/running/done/failed) and per-step duration. | Built | P1 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | UI-013
CA-007 | Change-Parameter Intent Execution | Chat intent like 'increase qRxLevMin by 2dB on USID 9787' triggers full pipeline — validate, draft, queue, push, monitor. | Built | P1 | Approved | Agent Team | L | v1.1 | Q2 2026 | CA-001, KN-002
CA-008 | Traffic Balancing Automation | Pre-built template for HOSR-driven balancing — picks neighbor relations, computes offsets, pushes through OSS. | Built | P1 | Approved | Agent Team | L | v1.1 | Q2 2026 | CA-001

## Knowledge Library
Knowledge Library
7 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
KN-001 | Telecom Knowledge Service | Q&A engine grounded in DataDict. Answers 'what is qRxLevMin?' with description, range, default, usage notes. | Built | P0 | Approved | Knowledge Team | L | v1.0 | Q1 2026 | KN-002
KN-002 | DataDict Resolver (16k Parameters) | In-memory index of 16,038 Ericsson EIAP telco_RAN parameters. Exact, prefix, fuzzy match. Disk-warmed on boot. | Built | P0 | Approved | Knowledge Team | L | v1.0 | Q1 2026 | —
KN-003 | Fuzzy Match KPI / Parameter Lookup | Trigram fuzzy match for misspelled/informal names. Returns ranked candidates with confidence. | Built | P0 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | KN-002
KN-004 | Knowledge Stream Chat | Dedicated chat stream routing all queries through knowledge tool. Answer cards with definition, range, related params. | Built | P1 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | CI-001, KN-001
KN-005 | Parameter-to-KPI Mapper | Reverse lookup — given a KPI, list parameters that influence it. 'Which parameters affect drop rate?' queries. | Built | P1 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | KN-002
KN-006 | Schema Registry | Backend cache of remote DB column types + KPI catalog. Refreshes hourly. Used by SQL generator. | Built | P1 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
KN-007 | CSV RAG Resolver | Retrieval-augmented resolver for CSV-uploaded scenario data. Answers about user's own data file. | Built | P2 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | —

## Generative UI
Generative UI
22 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
UI-001 | UiBlocksRenderer | Central renderer mapping every uiBlock type to a React component. 18+ types. Auto-pairs adjacent compact tables. | Built | P0 | Approved | Frontend Platform | L | v1.0 | Q1 2026 | —
UI-002 | data_table (AG-Grid) | Heavy interactive table with filter, sort, virtualization, Explain-RCA button. For multi-site lists. | Built | P0 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
UI-003 | compact_table | Lightweight dense table — auto numeric/cell-name/anomaly detection, no Explain button. For single-USID context. | Built | P0 | Approved | Frontend Platform | M | v1.2 | Q2 2026 | UI-001
UI-004 | kpi_dashboard | Interactive multi-KPI chart panel. Daily/hourly toggle, KPI selector, save-to-dashboard, collapse-after-N-groups. | Built | P0 | Approved | Frontend Platform | L | v1.0 | Q1 2026 | DL-015
UI-005 | insight_chart | Single ECharts panel with title, subtitle, full ECharts option object. Most flexible chart type. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
UI-006 | stat_row | Horizontal row of label/value stat tiles. Compact way to surface a handful of metrics. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
UI-007 | callout (toned info box) | Tone-colored box — info, success, warning, error. Icon + text. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
UI-008 | chips (interactive prompts) | Row of clickable pill buttons. Each chip emits a chat prompt. Used for KPI disambiguation. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
UI-009 | ranked_list | Vertical ranked list — severity dot, value, trend sparkline. Compact offender lists. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
UI-010 | rca_story | Narrative-style RCA card — chain-of-thought steps, evidence, conclusion. For summary-mode RCA views. | Built | P1 | Approved | Frontend Platform | L | v1.0 | Q1 2026 | UI-001
UI-011 | rca_summary / rca_report | Condensed RCA cards — bucket category, confidence score, short summary. First thing user sees on degraded site. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
UI-012 | ticket_escalation | Card prompting user to escalate finding to NOC. Pre-filled with site context. | Built | P2 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
UI-013 | execution_status | Live workflow status — stage list, current step, progress bar. Polls automation backend. | Built | P1 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | CA-004
UI-014 | tabs container | Tabbed UI block, each tab carrying its own list of nested blocks. Used by generate_report for multi-panel reports. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
UI-015 | grid_layout | Responsive 2/3/4-column grid container holding child blocks. Tools compose dashboards dynamically. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
UI-016 | map_inset | Inline Mapbox preview rendered inside a chat message. Used by set_map_layer and neighbor RCA flows. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001, OB-001
UI-017 | code_view | Syntax-highlighted code block with copy button. SQL output, generated rApp code, config YAML. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
UI-018 | DiagnosisCard | Severity hero strip + animated orb + 4 verdict-section cards. Auto-extracted from structured-synthesis markdown. | Built | P0 | Approved | Frontend Platform | L | v1.2 | Q2 2026 | CI-009, CI-010
UI-019 | SeverityMeter | Horizontal bar gauges — gradient red→green by magnitude, anomaly halo + shimmer. KPI impact subcomponents. | Built | P0 | Approved | Frontend Platform | M | v1.2 | Q2 2026 | CI-004
UI-020 | TopologyGrid | Cells grouped by band — palette-tinted band chips, hover-lift tiles, anomaly red ring + pulsing dot. | Built | P0 | Approved | Frontend Platform | L | v1.2 | Q2 2026 | CI-004
UI-021 | Save-to-Dashboard Modal | On any chart, save current config (siteId, KPIs, timeframe, daysBack) as named dashboard. localStorage persistence. | Built | P2 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | UI-004
UI-022 | Saved Dashboards Manager | Sidebar list of saved dashboards — one-click reload, rename, delete. | Built | P2 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | UI-021

## Data Layer
Data Layer
18 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
DL-001 | NaavikDBConnector | TypeScript port of Python remote DB connector. POSTs SQL to remote query endpoint, returns parsed rows. | Built | P0 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
DL-002 | Local Postgres Mirror Schema | Dedicated mirror.* schema in local PG holding faithful copies of 14 remote tables. Same names (lowercased). | Built | P0 | Approved | Backend Platform | L | v1.2 | Q2 2026 | —
DL-003 | Schema Discovery from MSSQL | Auto-generates DDL by reading INFORMATION_SCHEMA.COLUMNS. Maps MSSQL types to PG. Re-runs on every boot. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002
DL-004 | Offender-Only Mirror Strategy | Mirror contains only rows for offender USIDs (chain_of_thought IS NOT NULL). ~50-100 USIDs/day × 30 days. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002
DL-005 | 30-Day Backfill on First Boot | Non-blocking 30-day backfill on first start. Days run sequentially; tables in parallel batches of 4. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002, DL-003
DL-006 | Daily Incremental Sync (03:00 UTC) | Cron-style scheduler runs runForDate(yesterday) daily. Configurable via MIRROR_DAILY_HOUR_UTC env. | Built | P0 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-005
DL-007 | 30-Day Retention Sweep | After every daily sync, prunes rows older than 30 days. Bounded storage + fast queries. | Built | P0 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-006
DL-008 | USID Chunking for High-Cardinality Tables | hourly_intermediate_kpis chunks offender USIDs (5/chunk, 3 concurrent). Avoids 10-min query timeouts. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-005
DL-009 | SARGable Date Predicates | Mirror queries use date_id::date BETWEEN $1 AND $2 instead of CAST(DATE_ID AS DATE) =. Index-friendly. | Built | P0 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-002
DL-010 | Mirror Run Log | mirror.run_log records every (date, table) sync — row counts, durations, errors. Surfaced via /api/mirror/status. | Built | P1 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-005
DL-011 | Mirror Admin Endpoints | POST /api/mirror/backfill?days=30 and GET /api/mirror/status. JWT-protected. | Built | P1 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-010
DL-012 | mirrorOrRemote Query Router | Local-first generic helper. 0 rows or error → transparent remote fallback. Used by all site-analysis tools and KPI dashboard. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002
DL-013 | Legacy Schema Shims | Auto-created VIEWs (filtered_sites, cqx_offenders_truth_table, filtered_cell_*) over mirror with PascalCase aliases. | Built | P1 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002
DL-014 | Topology Cache | topology_cache_sites + topology_cache_sectors synced from remote every 6h. Drives map view (faster than mirror). | Built | P0 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
DL-015 | KPI Data Adapter | Service aggregating daily/hourly KPIs for dashboard. Mirror-first with remote fallback. | Built | P0 | Approved | Backend Platform | L | v1.0 | Q1 2026 | DL-001, DL-002
DL-016 | SQL Generator (Text-to-SQL) | LLM-driven SQL generator turning chat queries into safe read-only PG SQL against public-schema views. | Built | P1 | Approved | Knowledge Team | L | v1.0 | Q1 2026 | DL-013, DL-018
DL-017 | Conversation Context Store | PG-backed per-thread chat state. Multi-turn context across reloads. | Built | P1 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
DL-018 | DB Schema Reference Cache | Hourly-refreshed cache of distinct KPI names, subcomponent names, column lists. Used by SQL generator + resolver. | Built | P1 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —

## Settings
Settings
7 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
ST-001 | Settings Page (Tabbed) | Dedicated /settings view with tabs — User Profile, AppGen Config, KPI Library, App Permissions, System Preferences. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | —
ST-002 | AppGen Settings | Per-user defaults — preferred LLM model, K8s context, OSS adapter, default scaffold options. | Built | P1 | Approved | AppGen Team | M | v1.1 | Q2 2026 | ST-001
ST-003 | KPI Library | Edit standard KPI groups + custom user-saved KPIs. Persisted in PG. | Built | P2 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | ST-001
ST-004 | User-App Permission Matrix | Admin-only UI for grant/revoke per-user app access. Backed by user_app_permissions table. | Built | P1 | Approved | Backend Platform | L | v1.1 | Q2 2026 | ST-001, PF-003
ST-005 | Theme Toggle | Light / Dark / Auto switch. Auto follows OS preference. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | PF-006
ST-006 | Demo Mode Toggle | Master switch enabling dummifier across the app. localStorage-persisted. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | DM-001
ST-007 | Profile Management | User can update display name, email, notification preferences. | Planned | P3 | Pending | Frontend Platform | S | v1.4 | Q3 2026 | ST-001

## Demo Mode
Demo Mode
5 features
ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
DM-001 | Dummifier Provider | React context exposing dId(usid) to mask real USIDs as UST######. Wraps every visible USID in the app. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | —
DM-002 | Reverse Mapping for Chat | When user types UST###### in chat, unmapText() translates back to real USID before sending to backend. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | DM-001
DM-003 | Persistent Demo Toggle | Demo mode survives reloads via localStorage('naavik_dummifier_enabled'). Controlled from Settings. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | DM-001, ST-006
DM-004 | Auto-Register Real IDs | Whenever live sites list updates, MapDataContext registers all real USIDs with dummifier so reverse-lookup stays warm. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | DM-001
DM-005 | Settings Page Integration | Toggle surfaced as single switch in Settings → System Preferences with explanatory hint. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | ST-006

## All Features
Master Feature List (flat — sort and filter across all domains)
Domain | ID | Feature | Description | Status | Priority | Approval | Owner | Effort | Target Version | Target Quarter | Dependencies | Notes
Platform & Auth | PF-001 | JWT Login + 4-hour Persistent Session | Username/password login with bcrypt + JWT. Token stored in localStorage. Frontend re-verifies on reload. | Built | P0 | Approved | Auth Team | S | v1.0 | Q1 2026 | — | Live in prod
Platform & Auth | PF-002 | Env-Driven Admin Credentials | Admin user/password/JWT secret read from .env. Lazy init handles ESM hoisting timing. Fails fast on missing config. | Built | P0 | Approved | Auth Team | S | v1.0 | Q1 2026 | PF-001 | Hardened recently
Platform & Auth | PF-003 | Auth Context + Permission Gating | AuthContext exposes user + per-app permissions. Components gate features via useAuth(). Permissions auto-refresh on user change. | Built | P0 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | PF-001
Platform & Auth | PF-004 | First-Time Market Selector Modal | Non-dismissable modal blocks app on first login until market is picked. Subsequent logins skip it. Persisted to localStorage. | Built | P1 | Approved | Frontend Platform | S | v1.1 | Q2 2026 | PF-005
Platform & Auth | PF-005 | Multi-Market Configuration | Markets config in frontend/src/config/markets.ts. NorCal live; SoCal/PNW/TX/NE shown as 'Coming soon'. Maps labels to remote MARKET values. | Built | P1 | Approved | Frontend Platform | S | v1.1 | Q2 2026 | — | More markets pending data
Platform & Auth | PF-006 | Theme Provider (Light/Dark) | ThemeProvider exposes theme + setTheme. All bespoke components consume it. Defaults to dark; html.dark forced on bootstrap. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | —
Platform & Auth | PF-007 | User Profile Dropdown | Sidebar avatar opens consolidated menu — Market / Settings / Feedback / Logout. Inline when expanded; portal popover when collapsed. | Built | P1 | Approved | Frontend Platform | S | v1.1 | Q2 2026 | PF-005, ST-001
Platform & Auth | PF-008 | Collapsible Left Sidebar | Claude-style sidebar with collapse/expand, navigation rail, per-stream session history, profile menu at bottom. | Built | P1 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | —
Platform & Auth | PF-009 | Platform Bus (Inter-App Navigation) | Pub/sub bus for navigation intents (NAVIGATE_TO_APP). Shell subscribes and routes. Used by chat to deep-link into apps. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | —
Platform & Auth | PF-010 | App Registry | Dynamic registry of mountable apps with display name, icon, route, default chat stream, permission key. Drives sidebar nav and AppSlot. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | PF-009
Platform & Auth | PF-011 | Login UI with Fluid Background | Split-pane layout, animated fluid gradient background, theme-aware Naavik branding. Username + password + show/hide toggle. | Built | P2 | Approved | Design | S | v1.0 | Q1 2026 | PF-001
Chat & Intent | CI-001 | Multi-Stream Chat Orchestrator | Five chat streams (universal, observability, appgen, provision, knowledge) with stream-specific prompts and starter suggestions. | Built | P0 | Approved | Agent Team | M | v1.0 | Q1 2026 | —
Chat & Intent | CI-002 | Agent V3 Orchestrator | True OpenAI function-calling loop. Tools execute in parallel via Promise.allSettled. MAX_ITERATIONS=8, model gpt-4o-mini. | Built | P0 | Approved | Agent Team | L | v1.1 | Q2 2026 | —
Chat & Intent | CI-003 | 21-Tool Agent Registry | Tools include find_site, get_worst_offenders, RCA, KPI dashboard, query_data, generate_report, knowledge, navigation. | Built | P0 | Approved | Agent Team | L | v1.0 | Q1 2026 | CI-002
Chat & Intent | CI-004 | Site-Analysis Tool Suite (10 tools) | topology, config_changes, neighbor_relations, ret_changes, site_outages, neighbor_outages, hourly_trends, kpi_impact_breakdown, ticket_history, compare_with_cluster. | Built | P0 | Approved | Agent Team | XL | v1.1 | Q2 2026 | DL-002
Chat & Intent | CI-005 | Intent Classifier | Semantic + explicit + context-aware classifier. Routes 'show map', 'explain RCA', 'build app' to the right stream and tool path. | Built | P1 | Approved | Agent Team | M | v1.0 | Q1 2026 | —
Chat & Intent | CI-006 | Navigation Orchestrator | Three-layer intent detection turning chat into platform-bus events. 'Open observe' navigates; 'sites with alarms' also sets map layer. | Built | P1 | Approved | Agent Team | M | v1.0 | Q1 2026 | PF-009, CI-005
Chat & Intent | CI-007 | Conversation Context Service | Persists thread state, history, metadata in PostgreSQL. Multi-turn conversations work across reloads. | Built | P1 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
Chat & Intent | CI-008 | Stop Button (Abort Controller) | Send button morphs into Stop with spinning ring. Click aborts in-flight agentV3Chat via AbortController. Posts silent 'Request stopped' note. | Built | P1 | Approved | Frontend Platform | S | v1.2 | Q2 2026 | CI-002
Chat & Intent | CI-009 | Structured Synthesis Format | System prompt requires six-section markdown synthesis. Powers DiagnosisCard. Severity / Headline / What Changed / Degraded / Root Cause / Next Actions. | Built | P1 | Approved | Agent Team | S | v1.2 | Q2 2026 | CI-002
Chat & Intent | CI-010 | Auto-Emit Diagnosis Card | Orchestrator detects structured synthesis, injects diagnosis_card UI block, replaces chat-bubble text with just the headline. | Built | P1 | Approved | Agent Team | M | v1.2 | Q2 2026 | CI-009, UI-018
Chat & Intent | CI-011 | KPI / Parameter Resolver | resolve_kpi_param tool fuzzy-matches user phrases against the 16k DataDict catalog. Surfaces chip selector when ambiguous. | Built | P1 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | KN-002
Chat & Intent | CI-012 | Suggestion Chips & Starter Prompts | Each chat stream has curated suggestions. Empty state shows starter chips. Home rotates placeholders. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | —
Chat & Intent | CI-013 | Multi-Attachment Support | Up to 3 attachments per message — CSVs ≤750KB, images ≤900KB, text ≤120KB. Sent inline with chat payload. | Built | P2 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | —
Chat & Intent | CI-014 | Per-Stream Session History | Sidebar shows recent prompts grouped by stream. Click to re-send. History local to React state (not yet persisted). | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | — | Persistence planned for v1.3
Chat & Intent | CI-015 | V2 Chat Fallback | Legacy V2 orchestrator (no tool calling) as fallback. Toggle via localStorage or Settings. | Built | P3 | Approved | Agent Team | S | v0.9 | Q4 2025 | — | Will be deprecated in v2.0
Naavik Observe | OB-001 | Mapbox Site Map | Interactive Mapbox-GL map showing 6,800+ sites for selected market. Zoom/pan/click. Color-coded by severity. | Built | P0 | Approved | Observe Team | L | v1.0 | Q1 2026 | DL-014
Naavik Observe | OB-002 | Site Layer Toggles | Three layers — degraded, outage, overutilized. Driven by set_map_layer from chat or direct UI clicks. | Built | P0 | Approved | Observe Team | M | v1.0 | Q1 2026 | OB-001
Naavik Observe | OB-003 | Site Detail Panel — 5 Tabs | Click site → tabbed panel. Site KPI, RCA, Operational, Topology, AI Analyzer. Summary vs Diagnostic mode toggle. | Built | P0 | Approved | Observe Team | L | v1.1 | Q2 2026 | OB-001
Naavik Observe | OB-004 | Summary Mode (Animated RCA) | RCA-focused summary with step-by-step strongest-factors animation, mini-map for related neighbors. | Built | P1 | Approved | Observe Team | M | v1.0 | Q1 2026 | OB-003
Naavik Observe | OB-005 | Diagnostic Mode | Full telemetry — KPI charts, hourly insights, anomaly callouts. Sub-second loads via local mirror. | Built | P0 | Approved | Observe Team | L | v1.2 | Q2 2026 | DL-002, DL-012
Naavik Observe | OB-006 | Cell Topology View | Cells listed with band, technology, azimuth, height, anomaly. Replaced by TopologyGrid (band tiles). | Built | P1 | Approved | Observe Team | M | v1.2 | Q2 2026 | UI-020
Naavik Observe | OB-007 | KPI Dashboard (Daily/Hourly) | Multi-KPI line-chart with daily 7-90d / hourly 24-72h. KPI selector with 16 grouped standard KPIs + custom search. | Built | P0 | Approved | Observe Team | L | v1.0 | Q1 2026 | DL-015
Naavik Observe | OB-008 | Multi-KPI Comparison | Up to 8 KPIs simultaneously, unit-aware Y-axis, anomaly markers, shared 20-color palette. | Built | P1 | Approved | Observe Team | M | v1.0 | Q1 2026 | OB-007
Naavik Observe | OB-009 | Hourly Insights Panel | Time-of-day pattern analysis — peak hours, busy-hour deviation, anomaly hours, weekly comparison. | Built | P1 | Approved | Observe Team | M | v1.1 | Q2 2026 | OB-007
Naavik Observe | OB-010 | Mobility Trends | HOSR, inter/intra-frequency HO, throughput-per-handover. Used by analyzer for coverage detection. | Built | P2 | Approved | Observe Team | M | v1.1 | Q2 2026 | —
Naavik Observe | OB-011 | Outage Timeline | Per-cell outage events on 24h or 7d strip. Shows metric type and snapshot hour. | Built | P2 | Approved | Observe Team | M | v1.1 | Q2 2026 | —
Naavik Observe | OB-012 | Traffic Profile Dashboard | DL/UL volume + PRB-utilisation profile. Distinguishes capacity from coverage issues. | Built | P2 | Approved | Observe Team | M | v1.1 | Q2 2026 | —
Naavik Observe | OB-013 | Cross-Correlator (KPI Relationships) | Pairwise correlation between KPIs. Surfaces which pairs move together or diverge. | Planned | P2 | Pending | Observe Team | L | v1.4 | Q3 2026 | OB-007 | Removed for redesign
Naavik Observe | OB-014 | AI Analyzer Tab | Dedicated tab in site detail. Runs deep investigation (8-10 tools parallel). Hero severity card + 4 verdict sections + trail + evidence. | Built | P0 | Approved | Agent Team | L | v1.2 | Q2 2026 | CI-002, CI-004
Naavik Observe | OB-015 | Worst Offenders Ranking | Daily ranked list by total CQX impact. Each row links to site detail. Inline 'Explain RCA' button. | Built | P0 | Approved | Observe Team | M | v1.0 | Q1 2026 | DL-002
Naavik Observe | OB-016 | Cluster Comparison | Site KPI vs cluster peers. Returns rank, percentile, outlier flag (>2σ). Bar chart with source highlighted. | Built | P1 | Approved | Agent Team | M | v1.2 | Q2 2026 | CI-004
Naavik Observe | OB-017 | Neighbor Map Overlay | Top neighbors as dashed lines on map with HO-share labels. Click pivots panel to that site. | Built | P1 | Approved | Observe Team | M | v1.1 | Q2 2026 | OB-001, OB-003
Naavik Observe | OB-018 | Operational Info Workbench | Aggregates alarms, tickets, config, outages, EIM for site + neighbors over 7d. Sub-tabs per type. | Built | P1 | Approved | Observe Team | L | v1.1 | Q2 2026 | DL-002
Naavik Observe | OB-019 | Compass Dashboard (KPI Tiles) | Market-level dashboard tile grid showing aggregated KPIs across selected sites. At-a-glance Network Management home. | Built | P1 | Approved | Observe Team | M | v1.0 | Q1 2026 | DL-015
Naavik Observe | OB-020 | Telemetry Dashboard with Gauges + Heatmaps | Professional 5-tab telemetry — semicircular gauge charts, hourly heatmaps, KPI trend mini-charts. | Built | P1 | Approved | Observe Team | L | v1.1 | Q2 2026 | OB-007
Naavik Observe | OB-021 | Map Chat Bar | Persistent chat input docked to map view. Pre-fills with selected site's USID for quick 'what's wrong here?' queries. | Built | P1 | Approved | Observe Team | M | v1.0 | Q1 2026 | CI-001
Naavik Observe | OB-022 | Site Status Pills | TOP DEGRADED / OUTAGE pulse pills in panel header for offender sites. Pulled from cqx_offenders + site.outage. | Built | P2 | Approved | Observe Team | S | v1.0 | Q1 2026 | —
Naavik AppGen | AG-001 | 6-Stage AI App Pipeline | Planning → Code Gen → Audit → Unit Test → Integration → Assembly. State machine with backward navigation. | Built | P0 | Approved | AppGen Team | XL | v1.0 | Q1 2026 | —
Naavik AppGen | AG-002 | Planning Agent | Takes NL requirement, produces structured plan: target KPI, trigger, action, scope, failure modes. User approves before code gen. | Built | P0 | Approved | AppGen Team | L | v1.0 | Q1 2026 | AG-001
Naavik AppGen | AG-003 | Code Generation Agent | Generates rApp code, config YAML, K8s manifests, tests. Live file panel updates. Monaco editor for inline edit. | Built | P0 | Approved | AppGen Team | XL | v1.0 | Q1 2026 | AG-002
Naavik AppGen | AG-004 | Code Audit Agent | Static analysis — security (no embedded secrets, safe SQL), correctness (parameter ranges, KPI validity), style. | Built | P1 | Approved | AppGen Team | L | v1.0 | Q1 2026 | AG-003
Naavik AppGen | AG-005 | Unit Test Agent | Generates and runs unit tests in sandboxed runner. Failures surface inline with assertion details. | Built | P1 | Approved | AppGen Team | L | v1.0 | Q1 2026 | AG-003
Naavik AppGen | AG-006 | Integration Validation Agent | End-to-end smoke test against simulated network. Feeds rApp synthetic KPI streams, validates control actions. | Built | P1 | Approved | AppGen Team | L | v1.1 | Q2 2026 | PV-002
Naavik AppGen | AG-007 | App Assembly Agent | Packages code + tests + manifests + metadata into deployable bundle. Produces zip and 'publish to catalog' action. | Built | P1 | Approved | AppGen Team | M | v1.1 | Q2 2026 | AG-013
Naavik AppGen | AG-008 | Conversational App Builder | Free-form chat for app creation. Asks clarifying questions when requirement is ambiguous. | Built | P0 | Approved | AppGen Team | L | v1.0 | Q1 2026 | CI-001
Naavik AppGen | AG-009 | Scaffold Confirmation | Before code gen, agent shows file scaffold (which files, what they contain). User approves or rejects. | Built | P1 | Approved | AppGen Team | M | v1.0 | Q1 2026 | AG-002
Naavik AppGen | AG-010 | Real-Time File Generation Panel | Streamed file writes appear live. Each file shows progress + syntax-highlighted preview when done. | Built | P1 | Approved | AppGen Team | M | v1.0 | Q1 2026 | AG-003
Naavik AppGen | AG-011 | Workflow State Machine + Backward Nav | 6-stage pipeline persists per project. Rewind to any stage, edit, re-run forward. | Built | P1 | Approved | AppGen Team | L | v1.0 | Q1 2026 | AG-001
Naavik AppGen | AG-012 | Multi-Project Workspace | Side-by-side project switcher. Each project keeps own files, conversation, pipeline state. | Built | P2 | Approved | AppGen Team | M | v1.1 | Q2 2026 | AG-001
Naavik AppGen | AG-013 | rApp Packager | Produces Kubernetes-ready chart with values.yaml, deployment, service. Optional cluster-context targeting. | Built | P1 | Approved | AppGen Team | L | v1.1 | Q2 2026 | —
Naavik AppGen | AG-014 | AppGen Catalog with LangChain Reranker | Search-and-clone existing apps. Embeddings + LangChain rerank surface the most relevant prior art. | Built | P1 | Approved | AppGen Team | L | v1.1 | Q2 2026 | —
Naavik AppGen | AG-015 | YANG / DataDict Domain Tools | Validates parameters against YANG models and DataDict catalog. Surfaces 'unknown parameter' warnings. | Built | P1 | Approved | AppGen Team | M | v1.0 | Q1 2026 | KN-002
Naavik AppGen | AG-016 | Interactive Q&A Clarification | Planning agent asks user inline when requirement is unclear. Answers append to running plan. | Built | P1 | Approved | AppGen Team | M | v1.0 | Q1 2026 | AG-002
Naavik AppGen | AG-017 | AppGen Memory System | Per-project conversation memory + cross-project lessons learned. PG-backed, surfaced as suggestions. | Built | P2 | Approved | AppGen Team | M | v1.1 | Q2 2026 | —
Naavik AppGen | AG-018 | Agent Activity Rail | Live progress rail — current agent, tool called, time remaining. Useful for monitoring long pipelines. | Built | P2 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | AG-001
Naavik Provision | PV-001 | Provisioning Workflow Simulator | Simulates change-management — request, approval, OSS push, validation. No real network impact. | Built | P0 | Approved | Provision Team | L | v1.1 | Q2 2026 | —
Naavik Provision | PV-002 | OSS Adapter Framework | Pluggable connector interface for ENM, MOSES, etc. Simulator implements the same interface. | Built | P0 | Approved | Provision Team | L | v1.1 | Q2 2026 | —
Naavik Provision | PV-003 | ENM Connector | Direct integration with Ericsson Network Manager for parameter changes. Feature-flagged per market. | In Progress | P1 | Pending | Provision Team | L | v1.3 | Q3 2026 | PV-002 | Awaiting cred provisioning
Naavik Provision | PV-004 | Provisioning Candidate Site UI | Sites flagged for parameter changes with current vs proposed values, expected KPI delta, one-click submit. | Built | P1 | Approved | Provision Team | M | v1.1 | Q2 2026 | PV-001
Naavik Provision | PV-005 | Change Request Flow | Multi-step form: target sites, parameter, old/new values, justification, target window. Integrates rApp builder. | Built | P1 | Approved | Provision Team | L | v1.1 | Q2 2026 | PV-001, AG-001
Naavik Provision | PV-006 | Provisioning Status Tracking | Status board for in-flight, completed, failed changes. Each row exposes OSS audit log + rollback option. | Built | P1 | Approved | Provision Team | M | v1.1 | Q2 2026 | PV-001
Control Agent | CA-001 | Automation Pipeline Service | Backend orchestrator — chat-triggered intent → rApp build → OSS push → KPI validation. PG-persisted state. | Built | P0 | Approved | Agent Team | XL | v1.1 | Q2 2026 | CI-002, AG-001, PV-002
Control Agent | CA-002 | Workflow Generator | High-level goal → executable workflow JSON with steps, triggers, rollback logic. | Built | P1 | Approved | Agent Team | L | v1.1 | Q2 2026 | CA-001
Control Agent | CA-003 | OSS Adapter Simulator | In-process simulator mimicking OSS responses (success/failure, latency, parameter validation). Dev/demo safe. | Built | P1 | Approved | Provision Team | M | v1.1 | Q2 2026 | PV-002
Control Agent | CA-004 | Execution Status Polling | Polls automation status from backend at 2s intervals. Renders in WorkflowExecutionStatus UI block. | Built | P1 | Approved | Frontend Platform | S | v1.1 | Q2 2026 | CA-001, UI-013
Control Agent | CA-005 | Agent Automation Report | Final report after workflow — steps executed, OSS responses, KPI deltas measured, success/failure verdict. | Built | P1 | Approved | Agent Team | M | v1.1 | Q2 2026 | CA-001
Control Agent | CA-006 | Multi-Step Workflow Display | Stage-by-stage UI — each automation step with status (pending/running/done/failed) and per-step duration. | Built | P1 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | UI-013
Control Agent | CA-007 | Change-Parameter Intent Execution | Chat intent like 'increase qRxLevMin by 2dB on USID 9787' triggers full pipeline — validate, draft, queue, push, monitor. | Built | P1 | Approved | Agent Team | L | v1.1 | Q2 2026 | CA-001, KN-002
Control Agent | CA-008 | Traffic Balancing Automation | Pre-built template for HOSR-driven balancing — picks neighbor relations, computes offsets, pushes through OSS. | Built | P1 | Approved | Agent Team | L | v1.1 | Q2 2026 | CA-001
Knowledge Library | KN-001 | Telecom Knowledge Service | Q&A engine grounded in DataDict. Answers 'what is qRxLevMin?' with description, range, default, usage notes. | Built | P0 | Approved | Knowledge Team | L | v1.0 | Q1 2026 | KN-002
Knowledge Library | KN-002 | DataDict Resolver (16k Parameters) | In-memory index of 16,038 Ericsson EIAP telco_RAN parameters. Exact, prefix, fuzzy match. Disk-warmed on boot. | Built | P0 | Approved | Knowledge Team | L | v1.0 | Q1 2026 | —
Knowledge Library | KN-003 | Fuzzy Match KPI / Parameter Lookup | Trigram fuzzy match for misspelled/informal names. Returns ranked candidates with confidence. | Built | P0 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | KN-002
Knowledge Library | KN-004 | Knowledge Stream Chat | Dedicated chat stream routing all queries through knowledge tool. Answer cards with definition, range, related params. | Built | P1 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | CI-001, KN-001
Knowledge Library | KN-005 | Parameter-to-KPI Mapper | Reverse lookup — given a KPI, list parameters that influence it. 'Which parameters affect drop rate?' queries. | Built | P1 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | KN-002
Knowledge Library | KN-006 | Schema Registry | Backend cache of remote DB column types + KPI catalog. Refreshes hourly. Used by SQL generator. | Built | P1 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
Knowledge Library | KN-007 | CSV RAG Resolver | Retrieval-augmented resolver for CSV-uploaded scenario data. Answers about user's own data file. | Built | P2 | Approved | Knowledge Team | M | v1.0 | Q1 2026 | —
Generative UI | UI-001 | UiBlocksRenderer | Central renderer mapping every uiBlock type to a React component. 18+ types. Auto-pairs adjacent compact tables. | Built | P0 | Approved | Frontend Platform | L | v1.0 | Q1 2026 | —
Generative UI | UI-002 | data_table (AG-Grid) | Heavy interactive table with filter, sort, virtualization, Explain-RCA button. For multi-site lists. | Built | P0 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
Generative UI | UI-003 | compact_table | Lightweight dense table — auto numeric/cell-name/anomaly detection, no Explain button. For single-USID context. | Built | P0 | Approved | Frontend Platform | M | v1.2 | Q2 2026 | UI-001
Generative UI | UI-004 | kpi_dashboard | Interactive multi-KPI chart panel. Daily/hourly toggle, KPI selector, save-to-dashboard, collapse-after-N-groups. | Built | P0 | Approved | Frontend Platform | L | v1.0 | Q1 2026 | DL-015
Generative UI | UI-005 | insight_chart | Single ECharts panel with title, subtitle, full ECharts option object. Most flexible chart type. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
Generative UI | UI-006 | stat_row | Horizontal row of label/value stat tiles. Compact way to surface a handful of metrics. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
Generative UI | UI-007 | callout (toned info box) | Tone-colored box — info, success, warning, error. Icon + text. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
Generative UI | UI-008 | chips (interactive prompts) | Row of clickable pill buttons. Each chip emits a chat prompt. Used for KPI disambiguation. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
Generative UI | UI-009 | ranked_list | Vertical ranked list — severity dot, value, trend sparkline. Compact offender lists. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
Generative UI | UI-010 | rca_story | Narrative-style RCA card — chain-of-thought steps, evidence, conclusion. For summary-mode RCA views. | Built | P1 | Approved | Frontend Platform | L | v1.0 | Q1 2026 | UI-001
Generative UI | UI-011 | rca_summary / rca_report | Condensed RCA cards — bucket category, confidence score, short summary. First thing user sees on degraded site. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
Generative UI | UI-012 | ticket_escalation | Card prompting user to escalate finding to NOC. Pre-filled with site context. | Built | P2 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
Generative UI | UI-013 | execution_status | Live workflow status — stage list, current step, progress bar. Polls automation backend. | Built | P1 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | CA-004
Generative UI | UI-014 | tabs container | Tabbed UI block, each tab carrying its own list of nested blocks. Used by generate_report for multi-panel reports. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001
Generative UI | UI-015 | grid_layout | Responsive 2/3/4-column grid container holding child blocks. Tools compose dashboards dynamically. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
Generative UI | UI-016 | map_inset | Inline Mapbox preview rendered inside a chat message. Used by set_map_layer and neighbor RCA flows. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | UI-001, OB-001
Generative UI | UI-017 | code_view | Syntax-highlighted code block with copy button. SQL output, generated rApp code, config YAML. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | UI-001
Generative UI | UI-018 | DiagnosisCard | Severity hero strip + animated orb + 4 verdict-section cards. Auto-extracted from structured-synthesis markdown. | Built | P0 | Approved | Frontend Platform | L | v1.2 | Q2 2026 | CI-009, CI-010
Generative UI | UI-019 | SeverityMeter | Horizontal bar gauges — gradient red→green by magnitude, anomaly halo + shimmer. KPI impact subcomponents. | Built | P0 | Approved | Frontend Platform | M | v1.2 | Q2 2026 | CI-004
Generative UI | UI-020 | TopologyGrid | Cells grouped by band — palette-tinted band chips, hover-lift tiles, anomaly red ring + pulsing dot. | Built | P0 | Approved | Frontend Platform | L | v1.2 | Q2 2026 | CI-004
Generative UI | UI-021 | Save-to-Dashboard Modal | On any chart, save current config (siteId, KPIs, timeframe, daysBack) as named dashboard. localStorage persistence. | Built | P2 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | UI-004
Generative UI | UI-022 | Saved Dashboards Manager | Sidebar list of saved dashboards — one-click reload, rename, delete. | Built | P2 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | UI-021
Data Layer | DL-001 | NaavikDBConnector | TypeScript port of Python remote DB connector. POSTs SQL to remote query endpoint, returns parsed rows. | Built | P0 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
Data Layer | DL-002 | Local Postgres Mirror Schema | Dedicated mirror.* schema in local PG holding faithful copies of 14 remote tables. Same names (lowercased). | Built | P0 | Approved | Backend Platform | L | v1.2 | Q2 2026 | —
Data Layer | DL-003 | Schema Discovery from MSSQL | Auto-generates DDL by reading INFORMATION_SCHEMA.COLUMNS. Maps MSSQL types to PG. Re-runs on every boot. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002
Data Layer | DL-004 | Offender-Only Mirror Strategy | Mirror contains only rows for offender USIDs (chain_of_thought IS NOT NULL). ~50-100 USIDs/day × 30 days. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002
Data Layer | DL-005 | 30-Day Backfill on First Boot | Non-blocking 30-day backfill on first start. Days run sequentially; tables in parallel batches of 4. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002, DL-003
Data Layer | DL-006 | Daily Incremental Sync (03:00 UTC) | Cron-style scheduler runs runForDate(yesterday) daily. Configurable via MIRROR_DAILY_HOUR_UTC env. | Built | P0 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-005
Data Layer | DL-007 | 30-Day Retention Sweep | After every daily sync, prunes rows older than 30 days. Bounded storage + fast queries. | Built | P0 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-006
Data Layer | DL-008 | USID Chunking for High-Cardinality Tables | hourly_intermediate_kpis chunks offender USIDs (5/chunk, 3 concurrent). Avoids 10-min query timeouts. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-005
Data Layer | DL-009 | SARGable Date Predicates | Mirror queries use date_id::date BETWEEN $1 AND $2 instead of CAST(DATE_ID AS DATE) =. Index-friendly. | Built | P0 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-002
Data Layer | DL-010 | Mirror Run Log | mirror.run_log records every (date, table) sync — row counts, durations, errors. Surfaced via /api/mirror/status. | Built | P1 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-005
Data Layer | DL-011 | Mirror Admin Endpoints | POST /api/mirror/backfill?days=30 and GET /api/mirror/status. JWT-protected. | Built | P1 | Approved | Backend Platform | S | v1.2 | Q2 2026 | DL-010
Data Layer | DL-012 | mirrorOrRemote Query Router | Local-first generic helper. 0 rows or error → transparent remote fallback. Used by all site-analysis tools and KPI dashboard. | Built | P0 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002
Data Layer | DL-013 | Legacy Schema Shims | Auto-created VIEWs (filtered_sites, cqx_offenders_truth_table, filtered_cell_*) over mirror with PascalCase aliases. | Built | P1 | Approved | Backend Platform | M | v1.2 | Q2 2026 | DL-002
Data Layer | DL-014 | Topology Cache | topology_cache_sites + topology_cache_sectors synced from remote every 6h. Drives map view (faster than mirror). | Built | P0 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
Data Layer | DL-015 | KPI Data Adapter | Service aggregating daily/hourly KPIs for dashboard. Mirror-first with remote fallback. | Built | P0 | Approved | Backend Platform | L | v1.0 | Q1 2026 | DL-001, DL-002
Data Layer | DL-016 | SQL Generator (Text-to-SQL) | LLM-driven SQL generator turning chat queries into safe read-only PG SQL against public-schema views. | Built | P1 | Approved | Knowledge Team | L | v1.0 | Q1 2026 | DL-013, DL-018
Data Layer | DL-017 | Conversation Context Store | PG-backed per-thread chat state. Multi-turn context across reloads. | Built | P1 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
Data Layer | DL-018 | DB Schema Reference Cache | Hourly-refreshed cache of distinct KPI names, subcomponent names, column lists. Used by SQL generator + resolver. | Built | P1 | Approved | Backend Platform | M | v1.0 | Q1 2026 | —
Settings | ST-001 | Settings Page (Tabbed) | Dedicated /settings view with tabs — User Profile, AppGen Config, KPI Library, App Permissions, System Preferences. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | —
Settings | ST-002 | AppGen Settings | Per-user defaults — preferred LLM model, K8s context, OSS adapter, default scaffold options. | Built | P1 | Approved | AppGen Team | M | v1.1 | Q2 2026 | ST-001
Settings | ST-003 | KPI Library | Edit standard KPI groups + custom user-saved KPIs. Persisted in PG. | Built | P2 | Approved | Frontend Platform | M | v1.1 | Q2 2026 | ST-001
Settings | ST-004 | User-App Permission Matrix | Admin-only UI for grant/revoke per-user app access. Backed by user_app_permissions table. | Built | P1 | Approved | Backend Platform | L | v1.1 | Q2 2026 | ST-001, PF-003
Settings | ST-005 | Theme Toggle | Light / Dark / Auto switch. Auto follows OS preference. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | PF-006
Settings | ST-006 | Demo Mode Toggle | Master switch enabling dummifier across the app. localStorage-persisted. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | DM-001
Settings | ST-007 | Profile Management | User can update display name, email, notification preferences. | Planned | P3 | Pending | Frontend Platform | S | v1.4 | Q3 2026 | ST-001
Demo Mode | DM-001 | Dummifier Provider | React context exposing dId(usid) to mask real USIDs as UST######. Wraps every visible USID in the app. | Built | P1 | Approved | Frontend Platform | M | v1.0 | Q1 2026 | —
Demo Mode | DM-002 | Reverse Mapping for Chat | When user types UST###### in chat, unmapText() translates back to real USID before sending to backend. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | DM-001
Demo Mode | DM-003 | Persistent Demo Toggle | Demo mode survives reloads via localStorage('naavik_dummifier_enabled'). Controlled from Settings. | Built | P1 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | DM-001, ST-006
Demo Mode | DM-004 | Auto-Register Real IDs | Whenever live sites list updates, MapDataContext registers all real USIDs with dummifier so reverse-lookup stays warm. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | DM-001
Demo Mode | DM-005 | Settings Page Integration | Toggle surfaced as single switch in Settings → System Preferences with explanatory hint. | Built | P2 | Approved | Frontend Platform | S | v1.0 | Q1 2026 | ST-006